## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | 1 | 2
[7 empty] | 78 | 0 | 0
Application Management / Administration
1 | REQ1 | REQ1 - Model S | PDP | Release-1 | P1 | Completed
|  |  | PLP | Release-1 | P2 | Completed | 13
|  |  | Image Update | Release-1 | P2 | Completed | 13
13
2 | REQ2 | REQ2 - Model 3 | PDP | Release-1 |  | Completed | 13
|  |  | PLP |  |  | Completed
|  |  | Image Update |  | P1 | Completed | 13
3 | REQ3 | REQ3 - Model X | PDP | Release-2 |  | Completed | 13
|  |  | PLP | Release-2 | P2 | Completed
|  |  | Image Update | Release-2 |  | Completed
4 | REQ4 | REQ4 - Model Y | PDP | Release-2 | P1 | Completed
|  |  | PLP | Release-1 |  | Completed
|  |  | Image Update | Release-2 | P1 | Completed
5 | REQ5 | REQ4- CyberTruck | PDP | Release-1 | P1 | Completed
|  |  | PLP | Release-1 | P2 | Completed
Image Update
6 | REQ6 | REQ6 - DevOps | Ci/CD for Front-end react | Release-2 | P1 | Completed
|  |  | Firebase integration for react | Release-2 | P2 | Completed
|  |  | Signin/Signout Functionality in react | Release-2 | P2 | Completed
7 | REQ7 | REQ8 - FrontEnd | FrontEnd | Release-2 | P1 | Completed
|  |  | Header | Release-1 | P1 | Completed
|  |  | Footer | Release-1 | P1 | Completed
|  |  | Slidershow | Release-1 | P1 | Completed
|  |  | Booking Form | Release-1 | P1 | Completed
8 | REQ8 | REQ8-Register | Disabling password
Adding Cities
Adding Dealers
Time Slot
Adding Dropdown
9 | REQ9 | REQ9 - Home page | Removing Apparel store related images
Removing Navbar
Disabling Login
Adding car Details
Redirecting to Register page
Modifying the header
Modifying the footer
10 | REQ10 | REQ10-Restrictions | User
Booking
11 | REQ11 | REQ11-Email | Email validation
Confirmation of test drive booking
12 | REQ12 | REQ12-Fuctions | Disabling stock
Disabling add to cart feature
13 | REQ13 | REQ13-Devops | Configuring Sap project
configuring jenkins CI for sap hybris
Appling Deployment slot for React Front end
Maintaining CI/CD Pipeline
14 | REQ14 | REQ14-FrontEnd | Header
Footer
Home Page
Car Detail Pages
Test Drive Page
Booking Form
Validation
Responsive
Database Intergration
Manual Testing

## Burndown
Iteration | 0 | 2
Remaining | 78 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release