## Sprint-4.0 Retrospection
Project Name: XXXXX
Sprint - 4.0 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | 98% of the planned tasks are completed in Sprint - | Iteration backlog was not updated before standup meeting | Team Members should update iteration backlog before standup meeting | 30-March-2023 (Sprint - 1.0) | Team
2 | Team co-ordination is excellent |  |  | 30-March-2023 (Sprint - 1.0) | Team
3 |  | Time estimation was not planned effectively | Regrouping inorder to estimate proper estimation of time keeping in mind all the limittations | 30-March-2023 (Sprint - 1.0) | Team
4 | Working Azure CI and CD for Frontend | Road block in Jenkins integration | R&D | 30-March-2023 (Sprint - 1.0) | Team
5 |  | Building and server startup took more than estimated time |  | 30-March-2023 (Sprint - 1.0) | Team